Raspberry PI Blackbox
( Blackberry ?) Software
Timeline Estimates

Feb 13, 2020

Table of Contents
# Completed Already
## System Startup / Configuration
Functionality Completed:
- Execute shell commands from C program
- List Files and Folders in a given directory
- Retrieve Environment Variables
- Set Hostname
- Get Hostname
- Add User
- Enable Autologin for user
- Set password for user / change password
- Backup files before modifying
- List Users
- Create Aliases File
- Verify boot file configured properly
- Configure boot file
  - enable ssh
  - enable I2C
  - enable SPI
  - enable SPI1
  - disable bluetooth
  - Set language to US
  - Set US keyboard layout
# Software TO COMPLETE
## System Startup / Configuration
Time Estimate:	7 days
Tasks
- setup network
- setup automatic mounting of flash drive to predictable location
- setup automated install of bcm2835 library, and other needed libraries
- parse PI_BB.config file
- Set Environment Variables
- Look for attached Flash Drive, if detected mount it
- Look for Hub to Connect to
- Sync to Network time if Available, else sync to DS3231
- Send SSH keys to hub
- Load Calibration files
- Enumerate any profiles in USB flash drive , copy to local SD card

## Board Assembly & Bring Up
Time Estimate:	7 days
Tasks
- add through hole components
- add Pis to boards
- bring boards up and verify everything works
  - verify relay working properly
  - verify both ADCs working
  - verify PS working
  - verify DS3231 working properly
  - verify programmable load and AC power measurement
## Execution Engine
Time Estimate:	10 days
Tasks
- Modify current monolithic datalogging code into modular executable components.
- Integrate socket / profile command inputs to execution engine
## Log File
Time Estimate:	3-4 days
Tasks
- Implement Naming Convention (use hostname)
- Parse device ID’s from config file, include in header
- Format Metrics properly
- Implement writing of start/stop flags
- Connect to execution engine to record commands (issued from socket or profile file) in the log
- Upload log file to hub after test completion
- Implement log file refresh every day at 12AM
## Profile File
Time Estimate:	3 days
Tasks
- parse profile, include error checking for: correct syntax, valid time specs, valid commands
- Create mechanism to pass commands to execution engine
## Calibration
Time Estimate:	10 days
Tasks
- get code working to connect to 5335B (power meter) over USB
- code to connect to HP 34401’s via RS232
- code to connect to HP power supply E3648A
- put together code to calibrate a board -
  - set voltage to various settings, read back with 34401
  - adjust pots on pcb
  - run through multiple cooldowns, at various load levels, logging from power meter
  - use logged values vs reported to create a LUT
  - Use external 200 Ohm resistor, run through various load currents, logging with 34401, use logged vs reported to create LUT
  - write code to group sampled values and create LUT
  - write LUT to Cal file
## GUI
Time Estimate:	4-7 days
Tasks
- integrate GUI w/ execution engine, linking the metrics reporting to dynamic updated fields in GUI
- polish GUI interface

## Code Release
Time Estimate:	4-7 days
Tasks
- put together network with Pis and a hub
- test & verify everything is functional when integrated together
- patch any bugs
- finish up any requisite documentation